## L1 Checklists
Building | Room | Delivery | Form Number | Form Link | Completion Date | Progress | Status | Notes
RPL10 | 10EF1f | 1 | 6172 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/1b6121a6-ddaf-4b7f-9e21-2f8dfd45331e | 03/07/2026 | 100 | Complete
RPL10 | 10EF1f | 2 | 6175 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/53494497-c7f0-4da0-83eb-afd4cc9b7ccb | 03/06/2026 | 100 | Complete
RPL10 | 10EF1f | 3 | 6559 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/b820efba-14fc-487a-9c1e-011c6c6f11e3 | 04/17/2026 | 100 | Complete
RPL10 | 10EF1f | 4 | 6618 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/a6535bcb-49ca-443c-860e-eabbe68dce41 |  | 0 | Created
RPL10 | 10EF1f | 5 | 7181 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/ae543926-17f6-49a5-8930-b53765060222 | 05/01/2026 | 100 | Complete
RPL10 | 10EF1f | 6 | 7243 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/c0cad2f2-d779-437b-b031-9ce9d9a13881 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 7 | 7245 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/2d7106d7-9b1b-488e-9803-6883ee37e4c7 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 8 | 7246 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/4bd9303c-d955-411e-86a4-0f06d34e00f2 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 9 | 7250 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/dac87161-1d7b-429b-801c-a78e76e9975c | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 10 | 7251 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/3d816ef6-f1d2-4a3b-9da6-b1b4a2d5a448?referrer_url=https%3A%2F%2Facc.autodesk.com%2Fbuild%2Fforms%2Fprojects%2F62d30a4b-e399-4535-be39-dbd38e6aad35%2Ffield-reports%2F4949ca50-3508-5a31-a890-7d4130cebfc3%2Freports%2Fdac87161-1d7b-429b-801c-a78e76e9975c | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 11 | 7258 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/4b742b1e-f365-4519-9174-4f45affdb4d2 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 12 | 7260 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/b9bce230-3cd6-43ff-be6e-2e0bc1208a0d | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 13 | 7261 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/efc86ebc-eb4e-4283-999d-c91dc765c853 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 14 | 7266 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/b515b57a-c177-45a6-8bbb-5c14b3a7bf36 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 15 | 7277 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/b536e1f1-941e-4d2f-8306-d7969051f10c |  | 0 | Created
RPL10 | 10EF1f | 16 | 7281 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/1c188579-0b19-4017-93e3-cb978dcc8ec9 |  | 0 | Created
RPL10 | 10EF1f | 17 | 7275 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/086bcb0e-987b-40d5-b6a9-b0ed9f3fce92 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 18 | 7285 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/c966752d-549c-43a2-bf9e-4d5aa03a07f0 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 19 | 7290 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/84d2b848-b61e-4517-a817-e3a5ec6e8a3c | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 20 | 7292 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/9bb17b3c-a9aa-48cd-a6eb-61ef05829574 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 21 | 7288 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/a73f2f6f-c0c7-4fce-baef-192ac93c1ed9 |  | 0 | Created
RPL10 | 10EF1f | 22 | 7353 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/51198816-9d94-4db5-bde3-8e043da25f85 | 05/05/2026 | 100 | Complete
RPL10 | 10EF1f | 23 | 7361 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/97f2cfd6-4654-4302-864b-bb7bf41d66ea | 05/05/2026 | 100 | Complete
RPL10 | 10GSEF1 | 1 | 5950 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/2d6575fd-5945-4452-9fec-0da580326a45 | 03/26/2026 | 100 | Complete
RPL10 | 10GSEF1 | 2 | 5974 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/acc74eea-dfc5-4706-8b67-4e29243c29b0 | 04/01/2026 | 100 | Complete
RPL10 | 10GSEF1 | 3 | 6998 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/0317df31-ae6a-4a87-92b4-9e2e91cb6fcb | 04/29/2026 | 100 | Complete
RPL10 | 10GSEF1 | 4 | 7323 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/9229eed2-3aa5-4085-a1a3-5d2d60033401 | 05/05/2026 | 100 | Complete
RPL10 | 10GSMDF1 | 1 | 7249 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/c91f5a0e-c4bc-4579-8bff-a1541530b69b | 05/01/2026 | 100 | Complete
RPL10 | RPL10 NS1 MP01/02 CFD1 | 1 | 6314 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/08a39ddd-9a5d-559d-a3eb-b87abe6df3f9/reports/485e1dd9-c96a-4feb-883b-42e8ab0e6946 | 04/13/2026 | 100 | Complete
RPL10 | RPL10 NS1 MP01/02 CFD1 | 2 | 6991 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/2f70c6db-809f-4b05-9821-cbe87e303e8b | 04/29/2026 | 100 | Complete
RPL10 | RPL10 NS1 MP01/02 CFD1 | 3 | 6992 | https://acc.autodesk.com/build/forms/projects/62d30a4b-e399-4535-be39-dbd38e6aad35/field-reports/4949ca50-3508-5a31-a890-7d4130cebfc3/reports/cf68d29e-fbeb-41ac-a8df-a2cda91fac6e | 04/29/2026 | 100 | Complete